## Explanation
Project Management Tool
Look at the timelines on the following three spreadsheet in the tabs below and decide who is responsible for which tasks and decide on the due dates:
Sheet #1: Design
Sheet #2: Pedagogy
Sheet #3: trip Management

## Design
Trip Management and Logistics |  |  | Timeline | [5 empty] | Delegation |  |  |  | Progress
Category | Specifics | Details | 2 years | 1 year | 6 months | 3 months | 1 month | In- or post- | Bureau | Partner | Students | You | Date assigned | Date Due | Complete
1. Designing | a) Needs assessment | i. Determine the needs of all parties involved (students, teachers, ministerial objectives, department, college, other colleges, granting agencies, etc.) | [6 empty] | Jane | Jim |  |  | Feb 13 | May 1 | Y
ii. Create an odyssey plan
iii. Pitching and gaining buy-in (likely an interative process of multiple pitches/focus groups with department, international offices, admin and perhaps even students)
| b) Application for final approval | i. Obtain a copy of the form you must complete for final approval for international projects. Usually, once a project has been approved by the committee, a teaching liberations (0.2 over a semester) will be granted to plan the sojourn
ii. Submit the application
2. Gaining allies | a) Department | i. Find another facilitator to accompany you and one backup facilitator should one of you fall ill or be unable to facilitate. This is often required in the instition's sojourn application form
| b) International department | i. Plan a meeting your point person from the international department. Approach them with a list of tasks that will need doing and see how much can be delegated. Make sure deadlines are clear.
| c) Payment | i. Determine who, at your institution, will collect payments and set up an account for the trip
ii. Determine who, at your institution, will be able to make advance payments for your sojourn
| d) Legalities | i. Ask about liability/diligence and how to protect yourself. Ask if training is offered.

## Pedagogy
Trip Management and Logistics |  |  | Timeline | [5 empty] | Delegation |  |  |  | Progress
Category | Specifics | Details | 2 years | 1 year | 6 months | 3 months | 1 month | In- or post- | Bureau | Partner | Students | You | Date assigned | Date Due | Complete
3. School logistics | a) Paid classes | i. Make a list of suitable language schools
ii. Negotiate a contract (e.g., costs and payment schedule, number of class hours per day, types of learning activities, evaluation, etc.)
iii. Reserve the school and making a deposit
iv. Make final payment for the school
| b) Teach your own classes | i. Use our lesson planner to prepare your classes
ii. Find a suitable location (e.g., quiet, good wifi connection, central to homestays, etc.)
iii. Reserve the location (if necessary)
| c) Teaching online | i. Ensure students have access to phones/tablets/laptops
ii. Ensure students have access to adequate wifi at their accommodations
iii. Determine which lessons or learning activities will take place online
4. Volunteering/Internships | a) Finding placements | i. Make a list of suitable organizations (e.g., paying a volunteer pairing organization like International Volunteer Headquarters, using a matching service like Work Away or WOOFING, etc.)
ii. Negotiate a contract (e.g., costs and payment schedule, number of volunteer hours per day, types of duties to perform, performance review, etc.)
iii. Arrange pre-sojourn contact between students and placements via online platforms such as Teams, Zoom, etc. (synchronous or asynchronous, group or individual, teacher pre-meeting with volunteer placements, setting up rules and expectations, etc.)
| b) Booking | i. Make payment to reserve services
ii. Make final payment for volunteering / internships
5. Learning activities | a) Making a list | i. Determine which tourist destinations are a must-see / must-do for your trip for recruitment purposes
ii. Meet with students to add any must-see or must-do activities to the itinerary. (See the form provided on our website for students to propose activities)
iii. Finalize the itinerary (ideally done in collaboration with the students)
| b) Booking | i. Find a travel company that offers a suitable package or book on your own
ii. Make initial deposits to reserve places
iii. Make final payments (ideally, everything is purchased/booked in advance so that you have as little to pay onsite as possible)

## Trip Management
Trip Management and Logistics |  |  | Timeline | [5 empty] | Delegation |  |  |  | Progress
Category | Specifics | Details | 2 years | 1 year | 6 months | 3 months | 1 month | In- or post- | Bureau | Partner | Students | You | Date assigned | Date Due | Complete
6. Recruitment | a) Publicizing | i. Determine a time and location for first informational meeting (best done first so it can be included with all promotional material)
ii. Put a writeup in the school newsletter
iii. Present at open-doors nights
iv. Include the sojourn in institutional promotional material and prospectus (usually done with the communications department)
v. Promote on social media (usually done with the communications department)
vi. Invite other language teachers to promote the informational meeting in their language classes
vii. Put up posters
viii. Create a digital space (e.g., a Facebook page) with all of the important details (e.g., objectives, dates, approximate cost, how to apply, what to include in an application, etc.), your contact info and the application form
| b) Information meeting | i. Prepare a Powerpoint with all the important information (e.g., objectives, dates, approximate cost, how to apply, etc.). Post this to the shared digital space.
ii. Host the meeting. At the beginning of the meeting, take the time to establish your credibility (our research shows this will be important to group dynamics). Use this as an opportunity to vet students and to see how well they work with others. Make sure the objectives of the sojourn are clear so that only students whose personal objectives align will apply
| c) Applications | i. Use the Microsoft Forms template we provide to create an online application form. The advantage of using this form is that only complete applications with copies of passports and covid vaccine QR codes can be submitted. Students will need to use their school email address to be able to upload documents to the form since the setting "Only people in my organization can respond" will be on.
ii. Verify applications and select students who will make it to the next round
iii. Contact students who have submitted complete applications and who you would like to interview
iv. Conduct interviews (online or in person, group or individual). Use the guidelines suggested on our website to formulate interview questions
| d) First team meeting | i. Contact successful applicants to inform them of meeting time and place
ii. Meet: break the ice; plan a positive contract (see guidelines on our website); delegate activities and set deadlines; give instructions for deposits; plan first fundraiser
| e) Fundraiser | i. Host first fundraiser. This is seen as an ongoing part of the recruitement process (to be held before the purchase of plane tickets). Only after the first fundraiser should students be fully admitted into the program.
7. Air transportation | a) Purchasing airline tickets | i. Make a public offering for airline tickets. Three submissions are required. This is best done at least four months in advance so that prices don't change too much between the time of the submission and purchase. Students should be told that airline tickets are non-refundable.
ii. Purchase tickets. This is usually done with a school credit card. Tickets are usually non-refundable and students should know this prior to purchase.
8. Ground transportation | a) Airport pickup | i. Reserve transport from the airport to hostel or homestays
| c) Airport dropoff | i. Reserve transport to the airport from hostel or homestays
| d) Daily transportation | i. Reserve or plan public transit between learning activities, host families, volunteer placements, etc. If you are renting vehicles, there may be issues of liability and obtaining international driver's licenses to address.
| e) Printed and/or digital directions | i. Print maps and save digital maps (available offline) to your devices if you are driving, using public transit or walking between destinations
9. Lodgings (also below in "Bilateral exchanges" | a) Paid accomodations | i. Book youth hostels and airbnbs. Make sure to read reviews first and to check refund policies.
| b) Homestay | i. Cold call institutions at your target destination or find a suitable homestay organization. Often language schools and volunteer organizations also provide a homestay option at a reasonable cost (e.g., International Volunteer Headquarters, Work Away, WOOFING, etc.)
ii. Make initial deposit for accommodations
iii. Make final payment for accommodations
iv. Meet host families online (see our guidelines for making contact)
| c) Bilateral exchange | i. Find a partner. Use an organization or cold call / email institutions
ii. Negotiate dates, objectives (e.g., how many students will participate, when will you go, when will they come, how long will people stay, language goals, etc.), and begin making planning decisions (e.g., how regularly you will meet, who will plan what, etc.)
iii. Determine how many students each host family take, obligations of host families, how much time will be spent with partners in each destination, etc.)
iv. Have students submit profiles and begin matching students
v. Make pre-departure contact (synchronous or asynchronous, group or individual, teacher pre-meeting with host families, setting up rules and expectations, etc.)
10. Food | a) Determining needs | i. Determine approximately how many meals and snacks will be needed (including food in transit), as well as water bottles if necessary. (First draft is done early for budegting purposes)
ii. Calculate the approximate cost of daily meals. (Sites like Numbeo are helpful for this)
| b) Making plans | i. Check all dietary needs of students. (This should be in the application if you used the Microsoft Forms template we provide)
ii. Finalize meal/water planning. (This is done once the itinerary is finalized and plane tickets have been purchased)
iii. Make restaurant reservations. Set meals work well and can be arranged in advance if you know students' dietary restrictions. This facilitates payment. The alternative is to determine which kinds of payment each restaurant accepts and to pay onsite
11. Finances | a) Money collection | i. Make arrangements for money transfers into a specific account for the trip. Ensure that the person in charge has a list of the students, the amounts, and the deadlines for each of the transfers.
| b) Budgeting | i. Obtain a copy of the budgeting tool provided by your college (e.g., CLARA) and/or use the budgeting tool provided on our website. Complete the initial budget.
ii. Revise budget pre-departure.
| c) Payment (overseas) | i. Obtain a credit card from your international office or arrange to have the funds deposited to a shared account for the teachers
ii. Create a shared account for all facilitators for small cash expenses (if necessary)
iii. If a school credit card has not been supplied, formulate a plan for emergency expenses (e.g., hospital requires a credit card to proceed with treatment even if student has an insurance plan)
iv. Obtain approval to be reimbursed for increased cost for all facilitators' mobile phone plans or have school provide phones
v. Submit all personal expenses for reimbursement (e.g., vaccines, insurance, visas, phone plan, etc.)
| d) Grants | i. Determine if you are eligible for funding from Le Programme d'échanges et de séjours linguistiques à l'extérieur du Québec (PESLEQ) or from Global Skills Opportunity through Colleges & Institutes Canada (CICAN). This is best done at the earlies design stages.
ii. Submit completed application
| e) Funding from institutional organizations | i. Contact your institute's endowment foundation, coop and student association to see if they support overseas learning sojourns
ii. Submit letters of request
12. Trip preparation | a) Vaccines | i. Consult the Government of Canada Travel Advice & Advisories page to determine which pre-travel vaccines and medications are recommended: https://travel.gc.ca/travelling/health-safety/vaccines
ii. Enter pre-travel vaccines and medications into the Microsoft Forms form
iii. See application forms to determine which students still need which vaccines
iv. Make appointment for entire group through travel clinic or have students set deadline (the government of Canada recommends doing this at least six weeks before travel)
v. Get vaccinated
vi. Submit your vaccine receipts to insurance (if applicable)
| b) Insurance | i. See application forms to determine which students still need to purchase insurance
ii. Set meeting date for students to purchase insurance. All students must arrive at meeting with a credit card.
iii. Purchase insurance online. Know your dates. Include day of departure and day of arrival. (Teachers with the FNEEQ are not covered through Beneva for emergency medical insurance when traveling with students and must therefore purchase additional insurance)
| c) Visas | i. See application forms to determine which students will need to obtain visas. This is best done when purchasing plane tickets to determine if additional visas will be required for layovers (e.g., Students with Haitian passports require visas to complete a layover in the USA).
ii. Obtain all required visas (Canadia citizens can usually obtain visas on arrival in most countries or can apply online)
| d) Government of Canada | i. Register your stay abroad with the Canadian Government: https://travel.gc.ca/travelling/registration
ii. Verify travel advisories pre-departure and in-sojourn to ensure that the level does not exceed "Exercise a high degree of caution" (level 2). Most institutions will not sanction travel at levels higher than 2 since Levels higher than 2 impact insurance coverage and liability.
| e) Safety and cultural training | i. Determine if this is required by your institution
ii. Set date for training (if necessary)
iii. Complete training (if necessary)
13. Collating information | a) Folders | i. Create a shared online folder for all facilitators and for the international office
ii. Obtain a binder or folder for printed paper copies
| b) Students | i. Export all information from the Microsoft Forms applications into an Excel File and print the document as well as all uploaded material. Keep copies (digital and paper) in your folders
ii. Add scanned copies / printouts of vaccination information, visas and insurance purchased since applications to the folders
iii. Add signed copies of behavioural contracts to the folders
iv. Add signed copies of positive contracts to the folders
| c) School contacts | i. Obtain a contact number for your international office and your immediate superior. Discuss emergency protocols. Add this to your folders.
| d) Hospitals | i. Create a list of names and locations of top hospitals in your destination(s) and add to your folders
| e) Embassies/Consulates | i. Obtain the contact information for the nearest Canadian embassy or consulate and add to your folders